## Sheet1
Meeting Day TBD
Week 1 | Research and choose toys for Adaptathon (5 total, choose more than 5 for options)
Organize cart and take inventory of supplies (solder, batteries, sanding tools, etc.)
Put in order for test toys (2 each) and supplies ASAP
Week 2 | Decide on tenative total number of toys and how many of each button stand we need
Put in order for button stands ASAP (better to order too many than not enough)
Week 3 | If orders come in: Start working to adapt test toys
Take pictures to start making manuals for new toys
If no orders: No meeting
Week 4 | Start/continue working on test toys
Start/continue making manuals for new toys
Week 5 | Continue working on test toys and manuals
Organize new supplies on cart
Week 6 | Continue working on test toys and manuals
Start to finalize Adaptathon toy list
Week 7 | Finalize Adaptathon toy list
Put in big order for Adaptathon toys ASAP
Week 8 | Work on manuals
Week 9 | Work on manuals
Week 10 | Work on manuals
Week 11 | Wrap up